## Sheet1
| Date | 20/11/2023
| Project Mngr | Crăciun Albert | Name | Proiect MPS
Priority | PROJECT RISK MANAGEMENT PLAN
| Identification | [5 empty] | Qualitative Analysis | [9 empty] | Quantitative Analysis |  |  |  | Response Strategy |  |  | Monitoring and Control
| Status | ID # | Date Identified Project Phase | Functional Assignment | Threat | Risk Trigger (Event) Description | Type | Probability | Impact | Risk Matrix | [7 empty] | Probability (%) | Impact ($ or days) | Effect ($ or days) | Strategy | Response Actions including advantages and disadvantages | Affected WBS Tasks | Responsibilty (Task Manager) | Status Interval or Milestone Check | Date, Status and Review Comments
| Active |  | PID |  |  |  | Scope | Very High | Very High | [8 empty] | 0.9 |  |  | Avoidance
| Dormant |  | PA&ED |  |  |  | Schedule | High | High | [8 empty] | 0.7 |  |  | Transference
| Retired |  | PS&E |  |  |  | Cost | Moderate | Moderate | [8 empty] | 0.5 |  |  | Mitigation
|  |  | Construction |  |  |  | Quality | Low | Low | [8 empty] | 0.3 |  |  | Acceptance
[8 empty] | Very Low | Very Low | [8 empty] | 0.1 |  |  | N/A
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | [6 empty] | (12) |  | (13) | (14) =(13)x(12) | (15) | (16) | (17) | (18) | (19) | (20)
1 | Active | 1 | 18/10/2023 | Research | Meeting department members and project discution | Splitting the tasks between members | scope | Moderate | Very High | Probability | VH | [5 empty] | #REF! | 30% | 15 | 4.5 | Mitigation | Splitting the tasks between members by previous expirience |  | Whole team | 2 weeks
[11 empty] | H | [5 empty] | #REF!
[11 empty] | M |  |  |  |  | X | #REF!
(4): Research | L | [5 empty] | #REF!
[11 empty] | VL | [5 empty] | #REF!
[12 empty] | VL | L | M | H | VH
Impact
2 | Active | 2 | 2023-01-11 | Development Global and Local | Research + Coding | Bugs, possible corner cases, complexity | Quality | Moderate | Very High | Probability | VH | [5 empty] | #REF! | 40% | 5 | 2 | Transference | Motivation for meeting deadlines. Discussion with whole team, each one with their idea. |  | Team Leader and Developers | 1 month
[11 empty] | H | [5 empty] | #REF!
[11 empty] | M |  |  |  |  | X | #REF!
(4): Development | L | [5 empty] | #REF!
[11 empty] | VL | [5 empty] | #REF!
[12 empty] | VL | L | M | H | VH
Impact
(
3 | Active | 3 | 2023-12-12 | Design, User Interaction, Outputs | Meeting department members | Complexity, nor user friendly, too crowded | Quality | Low | Very High | Probability | VH |  |  |  |  | X | 0 | 25% | 4 | 1 | Mitigation | Discuss about how easier it is to be used. The output is enough/too big/insufficient |  | Development team | 2 weeks
[11 empty] | H | [5 empty] | 0
[11 empty] | M | [5 empty] | 0
(4): Design | L |  |  |  |  | X | 0
[11 empty] | VL | [5 empty] | 0
[12 empty] | VL | L | M | H | VH
Impact
4 | Dormant | 4 | 15/11/2023 | Technical, Risk, Analysis, Statistics Reports | Final evaluation and writing the reports | Possible overlooked issues, unsatisfactory complexity | Quality | Very Low | High | Probability | VH | [5 empty] | 0 | 10% | 20 | 2 | Mitigation | Testing every aspect of the application. Discuss every bug with developers. Application too slow does not meet the expectations. Needs to be updated. |  | Development team | 2 weeks
[11 empty] | H |  |  |  |  | X | 0
[11 empty] | M | [5 empty] | 0
(4): Testing + Reports | L | [5 empty] | 0
[11 empty] | VL |  |  |  | X |  | 0
[12 empty] | VL | L | M | H | VH
Impact